## Sheet1
Date | Name | Status | Work
29/9/2023 | Aaditya | Done | Define Scope
29/9/2023 | Aaditya | Done | Define Deliverables
29/9/2023 | Uttam | Done | Do meet and discuss
30/9/2023 | Aaditya | Done | Work Delegation
30/9/2023 | Uttam | Pending | PPT | This had been delayed to 8 october
30/9/2023 | Gunjan | Pending | Solution for Frontend
30/9/2023 | Uttam | Done | Solution for Frontend
30/9/2023 | Aaditya | Done | Handle all the solution content and make PPT
30/9/2023 | Palak | Pending | Help Aaditya to make PPT | This had been delayed to 8 october
30/9/2023 | Manan | Pending | Solution for Backend
30/9/2023 | Madhav | Pending | Solution for Backend
2023-01-10 | Uttam | Done | Do meet and discuss about solution
2023-01-10 | Aaditya | Pending | Create example of putting yourself into the situtation of passeange and employee of railway station
2023-01-10 | Palak | Pending | Create example of putting yourself into the situtation of passeange and employee of railway station
2023-01-10 | Manan | Pending | Create example of putting yourself into the situtation of passeange and employee of railway station
2023-01-10 | Madhav | Pending | Create example of putting yourself into the situtation of passeange and employee of railway station
2023-01-10 | Gunjan | Pending | Create example of putting yourself into the situtation of passeange and employee of railway station
2023-02-10 | Uttam | Done | Frontend scope
2023-02-10 | Aaditya | Pending | Design + Use Flow ( How to use appliation )
2023-02-10 | Palak | Pending | Design + Use Flow ( How to use appliation )
2023-02-10 | Manan | Pending | Functionality + Backend + Data
2023-02-10 | Madhav | Pending | Functionality + Backend + Data
2023-02-10 | Gunjan | Pending | Frontend scope